## airport
Airport
This board is where you share your project roadmap with your client. All your communication can be handled here. Invite your clients as guests to this board. This will save you a million unnecessary emails & phone calls so you can get on with doing great work.
STUCK
Name | Owner | Status | Client | Timeline - Start | Timeline - End | Approval
User Permissions |  | Stuck |  | 2017-03-12 | 2017-03-24
Auto Logout Feature |  | Stuck |  | 2017-03-12 | 2017-03-24
Data Modeling |  | Stuck |  | 2017-03-17 | 2017-03-24
Updated DB |  | Stuck |  | 2017-03-08 | 2017-03-24
User Specific Web Pages |  | Stuck |  | 2017-03-09 | 2017-03-26
Understanding the code base |  | Stuck |  | 2017-03-01 | 2017-03-15
ON TRACK
Name | Owner | Status | Client | Timeline - Start | Timeline - End | Approval
CRUD APP |  | Working on it |  | 2017-03-17 | 2017-04-03
Import CSV to DB |  | Working on it |  | 2017-03-13 | 2017-04-08
Dashboard Login |  | Working on it |  | 2017-03-17 | 2017-04-08
Styling and Presentation |  | Working on it |  | 2017-03-17 | 2017-04-08
Create Website Info Pages |  | Working on it |  | 2017-03-21 | 2017-04-08
Create API Functions for DB |  | Working on it |  | 2017-03-13 | 2017-04-08
Handle SQL errors |  | Working on it |  | 2017-03-17 | 2017-04-03
Completed
Name | Owner | Status | Client | Timeline - Start | Timeline - End | Approval
Use Cases |  | Done |  | 2017-02-01 | 2017-02-24 | Approved!
Captive Portal Website |  | Done |  | 2017-02-24 | 2017-03-07 | Approved!
Captive Portal Mockup |  | Done |  | 2017-02-20 | 2017-02-23 | Approved!
Python API Integration |  | Done |  | 2017-02-24 | 2017-03-07 | Approved!
Moderator Dashboard Template |  | Done |  | 2017-03-08 | 2017-03-13 | Approved!
First Database Implementation |  | Done |  | 2017-02-25 | 2017-03-07 | Approved!
Elicitation Plan |  | Done |  | 2017-02-01 | 2017-02-08 | Approved!
Talk with Dr. Nettey |  | Done |  | 2017-02-01 | 2017-02-08 | Approved!
Talk to Akron-Canton and Cleveland HopKins |  | Done |  | 2017-02-06 | 2017-02-22 | Approved!